## Progress Claims
Builder Progress Claims Register — Australian Construction 2026
Claim No. | Project Name | Client / Principal | Builder / Contractor | Site Location | ABN | Contract No. | Contract Value ($) | Claim Period Start | Claim Period End | Progress % This Claim | Previous Claim Value ($) | This Claim Value ($) | Variation / Extra Works ($) | Retention % | Retention Held ($) | GST 10% ($) | Total Claim Amount ($) | Payment Due Date | Status | Notes
PC-001 | Sydney CBD Commercial Tower | Olivia Brown Constructions | Jack Wilson Builders Pty Ltd | Sydney CBD | ABN 12 345 678 901 | CT-2026-001 | 850000 | 01/07/2026 | 31/07/2026 | 12% | 0 |  | 5000 | 5% |  |  |  | 14/08/2026 | Pending | First progress claim
PC-002 | Docklands Residential Complex | Charlotte Taylor Developments | Liam Smith Constructions | Docklands, Melbourne | ABN 23 456 789 012 | CT-2026-002 | 1200000 | 01/07/2026 | 31/07/2026 | 18% | 102000 |  | 0 | 5% |  |  |  | 15/08/2026 | Pending | Slab and framing complete
PC-003 | South Brisbane Mixed Use | Mia Williams Pty Ltd | Noah Johnson Builders | South Brisbane | ABN 34 567 890 123 | CT-2026-003 | 620000 | 01/08/2026 | 31/08/2026 | 22% | 74400 |  | 12500 | 5% |  |  |  | 14/09/2026 | Paid | Additional excavation works
PC-004 | Fremantle Warehouse Development | Ruby Martin Projects | Ethan Davis Construction | Fremantle, Perth | ABN 45 678 901 234 | CT-2026-004 | 980000 | 01/08/2026 | 31/08/2026 | 35% | 196000 |  | 0 | 10% |  |  |  | 16/09/2026 | Pending | Retention increased by contract
PC-005 | Norwood Retail Fit-Out | Isla Thompson Group | Cooper Anderson Builders | Norwood, Adelaide | ABN 56 789 012 345 | CT-2026-005 | 540000 | 01/09/2026 | 30/09/2026 | 40% | 162000 |  | 3750 | 5% |  |  |  | 14/10/2026 | Pending | Fit-out stage
PC-006 | Southport Mixed Development | Mia Williams Pty Ltd | Jack Wilson Builders Pty Ltd | Southport, Gold Coast | ABN 12 345 678 901 | CT-2026-006 | 1450000 | 01/09/2026 | 30/09/2026 | 48% | 435000 |  | 0 | 5% |  |  |  | 14/10/2026 | Overdue | Payment not received
PC-007 | Hamilton Industrial Shed | Noah Johnson Builders | Olivia Brown Constructions | Hamilton, Newcastle | ABN 23 456 789 012 | CT-2026-007 | 760000 | 01/10/2026 | 31/10/2026 | 55% | 285600 |  | 8200 | 5% |  |  |  | 14/11/2026 | Pending | Roof complete
PC-008 | Fyshwick Government Fitout | Liam Smith Constructions | Charlotte Taylor Developments | Fyshwick, Canberra | ABN 34 567 890 123 | CT-2026-008 | 690000 | 01/10/2026 | 31/10/2026 | 62% | 310500 |  | 0 | 5% |  |  |  | 15/11/2026 | Pending | Fitout 62% complete
PC-009 | Cairns Resort Renovation | Ruby Martin Projects | Ethan Davis Construction | Cairns, QLD | ABN 45 678 901 234 | CT-2026-009 | 430000 | 01/11/2026 | 30/11/2026 | 75% | 215000 |  | 6500 | 5% |  |  |  | 14/12/2026 | Pending | Facade works complete
PC-010 | Darwin Civic Centre Upgrade | Isla Thompson Group | Cooper Anderson Builders | Darwin City, NT | ABN 56 789 012 345 | CT-2026-010 | 1100000 | 01/11/2026 | 30/11/2026 | 80% | 638000 |  | 14000 | 5% |  |  |  | 15/12/2026 | Overdue | Defects liability review pending
TOTALS

## Summary Dashboard
Progress Claims — Summary Dashboard
Metric | Value
Total Contract Value ($)
Total Claimed to Date ($)
Total Variations ($)
Total Retention Held ($)
Total GST ($)
Total Claim Amount ($)
Average Progress % Per Claim
Number of Claims
Count — Overdue Claims
Count — Paid Claims
Count — Pending Claims
Claims Over $100,000 (Yes/No)
Claim Lookup — Enter Claim No. Below
Enter Claim No.: | PC-001
Project Name
Client / Principal
Total Claim Amount ($)
Payment Due Date
Status
Claim No. | Total Claim Amount ($) | Progress % | Status
PC-001
PC-002
PC-003
PC-004
PC-005
PC-006
PC-007
PC-008
PC-009
PC-010
Status | Count
Pending
Paid
Overdue

## Instructions
Builder Progress Claim Workbook — Instructions & User Guide
1. Purpose of this Workbook
| Overview | This workbook is designed for Australian builders, contractors, and project managers to record, calculate, and track progress claims under a construction contract. It supports compliance with Australian payment legislation including the Building and Construction Industry Security of Payment Act (SOPA).
| Financial Year | The Australian financial year runs from 1 July to 30 June. Ensure all claim dates and payment due dates align with the relevant contract period and financial year.
2. How to Enter a Progress Claim (Step-by-Step)
Step 1 | Open the "Progress Claims" sheet | Navigate to the Progress Claims sheet — this is the main working sheet for all claim entries.
Step 2 | Enter Claim Details (Yellow Cells) | Fill in all yellow-highlighted input cells: Claim No., Project Name, Client/Principal, Builder/Contractor, Site Location, ABN, Contract No., Contract Value, Claim Dates, Progress %, Previous Claim Value, Variations, Retention %, and Payment Due Date.
Step 3 | Review Calculated Fields | The following columns are automatically calculated — do NOT overwrite them: This Claim Value, Retention Held, GST 10%, Total Claim Amount, Status.
Step 4 | Set Status | Select the claim status from the dropdown in the Status column: Pending, Paid, or Overdue. The workbook will also auto-flag Overdue based on the Payment Due Date.
Step 5 | Check the Summary Dashboard | Navigate to the Summary Dashboard sheet to review totals, averages, and status counts. Enter a Claim No. in the yellow cell to perform a VLOOKUP and retrieve claim details.
Step 6 | Review Charts | Charts on the Summary Dashboard show: (1) Total Claim Amount by Claim No.; (2) Progress % across claims; (3) Status breakdown pie chart.
3. Key Australian Construction Finance Terms
| GST (10%) | Goods and Services Tax is levied at 10% on the value of each progress claim. It is added to the Total Claim Amount. Builders must hold a valid ABN and be registered for GST to charge GST on a tax invoice.
| Retention | A percentage (typically 5–10%) withheld from each progress payment as security against defects. Retention is released at practical completion or as specified in the contract.
| Variations / Extra Works | Additional work outside the original contract scope. Variations must be agreed in writing and supported by a variation order. They are added to the claim separately.
| Payment Due Date | Under SOPA, payment must be made within the period specified in the contract (typically 10–15 business days). If no date is specified, statutory time limits apply.
| ABN | Australian Business Number — a unique 11-digit identifier for all Australian businesses. Your ABN must appear on all tax invoices and progress claims.
| BAS | Business Activity Statement — lodged with the ATO (monthly or quarterly) to report GST collected and paid. Ensure progress claim GST amounts are reconciled with your BAS.
| PAYG | Pay As You Go withholding — relevant if subcontractors do not quote an ABN. In that case, 47% withholding applies.
| Superannuation | Builders must ensure superannuation contributions (currently 11.5% for FY2026) are paid for all eligible workers in each pay period. This is separate from the progress claim amount.
4. Colour Key
| Yellow (Input) | Cells highlighted in pale yellow are editable input fields. Enter your data here.
| Green (Positive) | Green highlighting indicates a positive Total Claim Amount or a Paid status.
| Red (Overdue/Negative) | Red highlighting indicates an overdue payment or a negative claim value. Investigate immediately.
| Teal (Header) | Teal/dark-teal rows are headers or section titles — do not edit.
| White/Light Blue (Rows) | Alternating row fills for readability — no special meaning.
5. Progress Claim Checklist
☐ | ABN Confirmed | Your ABN is valid and displayed on the claim/tax invoice.
☐ | Contract No. Referenced | The correct contract number is recorded against this claim.
☐ | Progress % Verified | Progress percentage has been assessed and agreed with the Superintendent or Principal.
☐ | Variations Documented | All variations and extra works are supported by a signed variation order.
☐ | Retention % Correct | Retention rate matches the contract (commonly 5% or 10%).
☐ | GST Calculated | GST at 10% is correctly calculated and included in the Total Claim Amount.
☐ | Payment Due Date Set | Payment due date is consistent with the contract payment terms and SOPA obligations.
☐ | Tax Invoice Issued | A valid tax invoice has been issued to the Principal/Client with all required details.
☐ | BAS Reconciliation | GST amount has been noted for inclusion in the next BAS lodgement.
☐ | Summary Dashboard Reviewed | The Summary Dashboard has been reviewed and all totals are correct before submission.
Disclaimer: This workbook is a template only. Always seek professional legal, accounting, or construction law advice for your specific circumstances. Verify all GST, superannuation, and SOPA obligations with your adviser or the ATO.