## Emergency Plan
Action ID | Preparedness Area | Task / Action | Responsible Person | Priority | Status | Due Date | Completed Date | Estimated Cost (AUD) | Actual Cost (AUD) | Completion % | Contact ID | Contact Phone | Notes / Evidence
A001 | Property preparation | Clear leaf litter and gutters at the Sydney property | Jack Wilson | High | Overdue | 2026-09-25 |  | 250 |  |  | C002 |  | Photograph cleared gutters and retain green waste receipt.
A002 | Evacuation | Confirm evacuation route and alternative route from Melbourne | Olivia Brown | High | Complete | 2026-09-30 | 2026-09-20 | 0 | 0 |  | C003 |  | Primary route and meeting point shared with household.
A003 | Water supply | Service water pump and fittings at the Adelaide property | Liam Nguyen | High | In Progress | 2026-10-05 |  | 480 | 220 |  | C006 |  | Pump booking confirmed; test run still required.
A004 | Livestock | Prepare livestock transport plan near Bendigo | Charlotte Smith | High | Not Started | 2026-10-10 |  | 900 |  |  | C003 |  | Confirm float access, agistment location and animal identification.
A005 | Emergency supplies | Assemble emergency kit for the Canberra household | Noah Taylor | Medium | Complete | 2026-10-15 | 2026-09-22 | 350 | 320 |  | C008 |  | Kit includes water, torch, radio, medicines and printed contacts.
A006 | Power and fuel | Check generator and fuel storage at the Newcastle property | Mia Johnson | High | In Progress | 2026-10-22 |  | 650 | 180 |  | C002 |  | Fuel storage inspection booked; confirm safe storage requirements.
A007 | Communications | Update family contact tree for the Brisbane household | Ethan Williams | Medium | Complete | 2026-10-29 | 2026-09-18 | 0 | 0 |  | C004 |  | Offline contact list saved to phones and printed.
A008 | Home safety | Inspect smoke alarms and replace batteries in Hobart | Ruby Martin | High | Overdue | 2026-11-02 |  | 160 |  |  | C007 |  | Arrange qualified inspection if any alarm fails test.
A009 | Pets | Confirm pet accommodation near Wollongong | Cooper Davis | Medium | In Progress | 2026-11-08 |  | 120 | 50 |  | C002 |  | Confirm vaccination records, carrier and transport arrangements.
A010 | Warnings | Save local fire service warning sources for the Perth property | Isla Wilson | Low | Not Started | 2026-11-15 |  | 0 |  |  | C005 |  | Enable official warning app notifications and radio frequency details.
Operational totals |  |  |  | Completed actions |  | High-priority actions
This template supports planning only. In an emergency, call Triple Zero (000), follow advice from your state or territory fire service, and evacuate early when directed.

## Contacts
Contact ID | Organisation / Person | Contact Type | State / Territory | Location | Phone | Website / App | Notes
C001 | Emergency services | Emergency | Australia-wide | Australia-wide | 000 | triplezero.gov.au | For life-threatening emergencies only. Call Triple Zero (000).
C002 | NSW Rural Fire Service | Fire service | NSW | Sydney | 1800 679 737 | rfs.nsw.gov.au | Verify the local district contact details and current warning channels.
C003 | Country Fire Authority | Fire service | VIC | Melbourne | 1800 226 226 | cfa.vic.gov.au | Verify local fire danger ratings, warnings and community information.
C004 | Queensland Fire and Emergency Services | Fire service | QLD | Brisbane | 13 74 68 | qfes.qld.gov.au | Verify the local area contact details before bushfire season.
C005 | Department of Fire and Emergency Services | Fire service | WA | Perth | 13 33 37 | dfes.wa.gov.au | Use official warnings and verify local emergency contact arrangements.
C006 | South Australia Country Fire Service | Fire service | SA | Adelaide | 1300 362 361 | cfs.sa.gov.au | Verify the local CFS district and relevant warning sources.
C007 | Tasmania Fire Service | Fire service | TAS | Hobart | 1800 000 699 | fire.tas.gov.au | Confirm local fire weather, warnings and evacuation information.
C008 | Local vet / animal shelter | Animal support | ACT | Canberra | Verify locally | act.gov.au | Replace with your nearest animal support service and confirm availability.
Important | Contact details must be verified for your local area before each bushfire season and whenever circumstances change.

## Dashboard
Bushfire Emergency Plan Dashboard
This template supports planning only. In an emergency, call Triple Zero (000), follow advice from your state or territory fire service, and evacuate early when directed.
Total actions |  | Completed actions | Overall completion | Outstanding high-priority actions
Estimated preparedness cost |  | Actual spend | Budget variance | Overdue actions
Action status summary | Actions
Not Started
In Progress
Complete
Overdue
[5 empty] | Preparedness Area | Estimated Cost | Actual Cost | Responsible Person | Completion %

## Instructions
Bushfire Emergency Plan Workbook Instructions
Planning disclaimer | This template supports planning only. In an emergency, call Triple Zero (000), follow advice from your state or territory fire service, and evacuate early when directed.
Topic | Guidance
Customise actions | Update the Emergency Plan with property-specific actions, responsible people, due dates, evacuation routes and safe meeting locations. Pale yellow cells are intended for user input; blue cells contain calculated values.
Maintain contacts | Replace sample contacts with verified local fire service, council, neighbour, medical, school, workplace, animal support and accommodation contacts. Check phone numbers, websites and warning apps before each bushfire season.
Record household needs | Use the Notes / Evidence column to record household members, medicines, mobility or accessibility needs, essential documents, communications requirements and arrangements for children or visitors.
Plan for livestock and pets | Record transport, identification, feed, water, carriers, agistment, animal shelter and veterinary arrangements. Confirm that evacuation destinations can accept animals before an emergency.
Follow official warnings | Monitor official warnings from the relevant state or territory fire service. Follow local advice, fire danger ratings, road closures and evacuation directions. Do not rely on this workbook as a live warning source.
Leave early | Agree evacuation triggers in advance and leave early when directed or when conditions become unsafe. Call Triple Zero (000) for life-threatening emergencies. Keep printed and offline copies accessible.
Review regularly | Review the plan before each bushfire season and after any property change, household change, contact change, new livestock or pet arrangement, or bushfire event. Record evidence and costs as actions are completed.
Workbook sheets | Emergency Plan: action register and costs. Contacts: emergency and support directory. Dashboard: summary, alerts and charts. Instructions: planning guidance.